## Weekly Gantt Chart Template
WEEKLY GANTT CHART
| PROJECT: |  | Knowledge Competition
| Project Manager: |  | İbrahim-Bahadır-Gürkan
[5 empty] | 2023-04-07 | 2023-04-14 | 2023-04-21 | 2023-04-28 | 2023-05-05 | 2023-05-12 | 2023-05-19 | 2023-05-26 | 2023-06-02 | 2023-06-09 | 2023-06-16 | 2023-06-23 | 2023-06-30 | 2023-07-07 | 2023-07-14 | 2023-07-21
Task name | Stard date | End date | Assigned | Progress | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12 | WEEK 13 | WEEK 14
PLANNING | 2023-04-07 | 2023-04-27 | Group | 100% | bar: 2023-04-07 to 2023-04-14
Needs Assessment | 2023-04-07 | 2023-04-20 | Group | 100%
Project Agreement | 2023-04-20 | 2023-04-27 | Group | 100%
DESIGN | 2023-04-20 | 2023-05-13 | Group | 100%
Wireframe | 2023-04-27 | 2023-05-01 | Group | 100%
Mock ups+ Rewiew | 2023-04-27 | 2023-05-07 | Group | 100%
Slice and Code | 2023-04-30 | 2023-05-13 | Group | 100%
DEVELOPMENT | 2023-05-13 | 2023-06-13 | Group | 100%
Framework | 2023-05-13 | 2023-05-21 | Group | 100%
Page Templates | 2023-05-21 | 2023-05-30 | Group | 100%
Load + Edit Content | 2023-05-30 | 2023-06-08 | Group | 100%
Testing | 2023-06-08 | 2023-06-13 | Group | 100%
LAUNCH | 2023-06-08 | 2023-06-24 | Group | 100%
Rewiew + Refine | 2023-06-08 | 2023-06-12 | Group | 100%
Cross Browser Check | 2023-06-12 | 2023-06-18 | Group | 100%
Mobile Testing | 2023-06-18 | 2023-06-24 | Group | 100%
POST LAUNCH | 2023-06-24 | 2023-07-13 | Group | 100%
Assessment of Criticism | 2023-06-24 | 2023-07-13 | Group | 99%

## Useful Tips
USEFUL TIPS
1 | When enteringactivity start and end dates in columns "D" and "E" use the following date format: DD/MM/YYYY
2 | To change colour of fill and text in cells, use HOME -> FONT tool palette.
3 | To change LOGO image, right click on it and choose CHANGE PICTURE.

## ©
© TemplateLab.com